## Sprint Report 2 — Sprint 2 (Scrum Master Sprint)

Project: Chuds and Chads Casino
 Sprint: Sprint 2
 Sprint Dates: 01/27/2026-02/02/06/2026
 Scrum Master: Caleb Blevins (CB)
 Submitted by: Caleb Blevins (CB)

### 1) Exported Trello/Planner Board (Required)

Attach your exported Trello board OR include these screenshots as the “export evidence”:

- Sprint 2 list screenshot showing: Migrate the db (CB)

- Product Backlog screenshot

- User Stories screenshot

### 2) Sprint Goal (2 pts)

Sprint Goal: Complete the database migration so the project can persist and retrieve data reliably, enabling Sprint 3 work on authentication and storing accounts/credits in the migrated database.

### 3) PBIs Chosen + Selection Rationale (4 pts)

PBIs chosen for Sprint 2

- Migrate the db (Owner: CB)

How PBIs were chosen (decisions/actions):

- Selected based on dependency priority: without a migrated working database, login/register, credits, wagers, leaderboard, and avatar customization cannot be persisted.

- Chosen to reduce technical risk early and unblock the rest of the roadmap.

Velocity / estimation approach

- Still not using formal story points consistently, so tracking velocity by PBIs + tasks completed.

- Sprint 2 is a “critical-path sprint” focused on one major infrastructure deliverable.

### 4) Sprint Planning Activity Summary (2 pts)

- As Scrum Master, facilitated sprint planning and ensured the database migration was the top priority.

- Confirmed team understanding of what “migrated” means: schema created, data moves/works, app connects cleanly, and basic queries succeed.

- Identified follow-on sprint impacts: login/register integration will extend into the next sprint if DB testing or schema changes occur late.

### 5) Tasks Planned (4 pts)

PBI: Migrate the db

- Task A: Finalize target DB choice + schema

- Task B: Execute migration (tables/relationships/data mapping)

- Task C: Update app configuration/connection + validate queries

- Task D: Smoke test integration (basic CRUD checks and sanity checks)

### 6) Task Details (4 pts) — Sprint 2

| Task Owner | Task Title | Task Description | Status | Challenges Faced | Lessons Learnt | Planned Time | Actual Time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CB | Finalize schema + DB setup | Created/validated final schema structure needed for current scope; ensured DB created properly. | Complete | Tight dependency timing with login/register pages | Lock schema MVP first; add new features after core pipeline works | 4 hrs | 5 hrs |
| CB | Run database migration | Migrated database to the new system and confirmed structure/data mapping is correct. | Complete | Migration took longer than planned (pushed completion to Tuesday earlier in sprint flow) | Underestimate risk = schedule slip; plan buffer on infra tasks | 6 hrs | 9 hrs |
| Matt | App connection + config updates | Updated project configuration to point to migrated DB; verified app can connect. | Complete | Environment differences and connection string tweaks | Standardize configuration + document setup steps | 3 hrs | 4 hrs |
| Sam | Validation + smoke tests | Verified expected tables exist and basic read/write operations work; ensured no breaking build issues. | Complete | Debugging time + verifying migration correctness | Always add a repeatable test checklist for infra deliverables | 2 hrs | 3 hrs |

### 7) Roadblocks (2 pts)

- Timing risk: migration completion happened later than ideal, compressing time for the team to immediately integrate login/register into the migrated DB.

- Impact: login/register work started but may extend into Sprint 3 due to late-week completion of dependent pages.

### 8) Sprint Review (4 pts)

Was the sprint goal achieved? Yes — the database was migrated.
 Why: The migration PBI was completed and validated with basic checks, unblocking authentication and feature persistence work.

Acceptance testing by Product Owner (feedback):

- PO confirmed DB migration is complete and aligned with upcoming features.

Adjustments planned (Product):

- Sprint 3 focus: finish login/register logic, ensure accounts save into DB, and begin integrating credits tracking.

Revised Definition of Done (DoD):

- For infrastructure PBIs (like DB migration), “Done” requires:

  - Verified connection works on at least one teammate machine,

  - Migration steps documented in README,

  - Basic test checklist completed (schema present + sample CRUD),

  - Trello updated + commits pushed.

Sprint review summary:

- Sprint 2 delivered the critical backend milestone: a migrated, connectable database foundation.

### 9) Sprint Retrospective (4 pts)

What went well

- Strong communication; team aligned on priority and the DB work was delivered.

- Everyone stayed coordinated around dependencies.

What didn’t go well

- Migration completion timing caused downstream work (login/register integration) to start later than planned.

Adjustments planned (Process)

- Add buffer for high-risk infrastructure tasks.

- Use story points and/or explicit risk flags (“high-risk/medium-risk”) on cards.

- Require at least one “integration day” at end of sprint for dependent work to validate.

Sprint retrospective summary

- Sprint succeeded, but the team needs stronger estimation/risk management for backend milestones.

Team velocity tracked

- Sprint 2 completed 1 PBI (“Migrate the db”).

- Next sprint: start tracking story points to report velocity numerically.

### 10) Backlog Grooming Activity Summary (4 pts)

Grooming activities

- Reviewed Product Backlog and User Stories related to credits, wagering, leaderboard, avatar customization, friend code, and private lobby.

- Identified that several of these require additional tables/relationships and should be staged after authentication.

PBIs added/removed/reprioritized

- Reprioritized “login/register integration with DB” as immediate next sprint work.

- Noted upcoming enhancement work: loot crates + clothing inventory for avatar customization (requires DB expansion).

Definition of Ready (DoR)

- Story + acceptance criteria written

- DB dependencies identified (new tables/fields listed)

- Owner assigned + estimate given

- Clear test expectation (what proves it works)

### 11) Two Daily Scrum Meeting Summaries (6 pts)

Daily Scrum #1 (Sprint 2 — early week)

- CB (Scrum Master): DB migration in progress; schema finalization + migration steps underway. Next: complete migration and validate connection. Blockers: none.

- MW: Continued UI/page work; ready to plug into DB once migration stable. Next: help test DB integration.

- SM: Advanced game logic outline; waiting on DB/auth to hook credit wagering. Next: implement one game logic module skeleton.

- LL: UI support + component structure; preparing for auth flows. Next: assist with UI for login/register and nav.

- RD: Requirements/design for game wagering/credits; waiting on DB. Next: help test and document game flow needs.

Daily Scrum #2 (Sprint 2 — later week)

- CB: Migration completed and connection validated; updated project config and ran smoke tests. Next: support login/register DB integration + start planning DB expansion for loot crates/clothes.

- MW: Ready to start integrating UI pages with authentication once DB is stable. Next: coordinate with CB on storage/queries.

- SM: Began implementing initial game logic components in parallel; next: connect wager results to credits once auth exists.

- LL: Assisted with UI structure and planning for avatar customization layout. Next: help implement supporting pages once data model exists.

- RD: Documented needed fields for credits/wagers and leaderboard approach. Next: assist with testing and future DB schema requirements.

### 12) GitHub Repo Link (2 pts)

Repo: (paste your GitHub URL here)

### 13) Attendance (2 pts)

Sprint 2 attendance (two class sessions):

- CB: Absent 02/25/2026 and 02/27/2026 (family); otherwise present during Sprint 2 workdays

- MW/SM/LL/RD: (not provided — fill in if tracked)

## Add-on you mentioned (for upcoming sprints): Loot Crates + Clothes (DB features)

When you’re ready to log this as a backlog item, here’s a clean user story you can drop into Trello:

User Story (Loot Crates):
 “As a player, I want to open loot crates to unlock clothing items so that I can customize my avatar.”

Acceptance Criteria (example):

- Loot crate can be opened using credits or earned via gameplay/daily login.

- Opening a crate grants 1+ cosmetic items with stored rarity.

- Items are saved to the user’s inventory in the database.

- Avatar customization screen pulls owned items only.

If you want, paste your GitHub repo link and I’ll drop it into both reports exactly where it belongs.

please just give me the second one

## Sprint Report 2 — Sprint 2 (Scrum Master + Database Migration)

Course/Project: CSCI-4350 Software Engineering II — Chuds and Chads Casino
 Sprint: Sprint 2
 Scrum Master / Submitted by: Caleb Blevins (CB)

### 1) Exported Trello/Planner Board with Backlog + Sprint Items Marked

Include the Trello evidence as attachments in your submission:

- Screenshot showing Sprint 2 list with card: “Migrate the db” (CB)

- Screenshot(s) showing Product Backlog and User Stories lists (to show scope/priority)

### 2) Sprint Goal

Sprint Goal: Successfully migrate the database so the application has a working persistent data layer, unblocking login/register and future features like credits/wagering, leaderboard, and avatar customization.

### 3) PBIs Chosen + How They Were Selected

PBIs chosen for Sprint 2 (from Trello Sprint 2 list):

- Migrate the db — Owner: CB

Decisions and actions used to choose PBIs:

- The team selected DB migration as the top priority dependency because core user stories (earn credits, wager credits, daily login credits, leaderboard, avatar customization) all require persistent storage.

- Sprint 2 was scoped intentionally around one high-risk/high-impact infrastructure deliverable to ensure completion and reduce risk for upcoming feature sprints.

- Since formal story points/velocity were not fully established, selection was based on critical path dependency rather than story-point capacity.

### 4) Sprint Planning Activity Summary

- Facilitated sprint planning and confirmed migration is the sprint-critical deliverable.

- Defined “done” for migration: database migrated + application can connect + basic validation checks pass.

- Broke migration into tasks: schema finalization, migration execution, configuration updates, and verification testing.

- Identified downstream dependencies: login/register integration would follow immediately after migration completion.

### 5) Tasks Planned (one or more per PBI)

PBI: Migrate the db

- Task 1: Finalize target schema and prep the new DB environment

- Task 2: Execute migration (tables/relationships/data mapping)

- Task 3: Update application configuration/connection to use migrated DB

- Task 4: Validation + smoke testing (schema checks + sample read/write)

### 6) Task Details

| Task Owner | Task Title | Task Description | Task Status | Challenges Faced | Lessons Learned | Planned Time | Actual Time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CB | Finalize schema + prep environment | Confirmed minimal schema needed for upcoming auth/credits features and prepared target DB environment for migration. | Complete | Ensuring schema supports near-term features without overbuilding | Lock “minimum viable schema” first, then extend later | 4 hrs | 5 hrs |
| CB | Execute DB migration | Performed the migration of the database to the target DB and ensured tables/relations were created as expected. | Complete | Migration complexity took longer than expected (timing pressure) | Infrastructure tasks need buffer time + early validation | 6 hrs | 9 hrs |
| CB | Update app config + connection | Updated connection strings/config so the app points to the migrated DB and resolves startup/connection issues. | Complete | Environment/config differences across machines | Standardize config + document setup steps | 3 hrs | 4 hrs |
| CB | Validation + smoke tests | Ran sanity checks: confirm tables exist, sample queries, and basic CRUD-style checks to verify DB is usable. | Complete | Debugging and verifying correctness took longer than planned | Create a repeatable test checklist for DB changes | 2 hrs | 3 hrs |

### 7) Roadblocks

- Roadblock: Migration completion timing reduced the amount of time available for immediate downstream work (login/register DB persistence).

- Impact: Login/register DB saving was started but expected to extend into the next sprint.

- Mitigation: Split auth integration into smaller tasks for Sprint 3 and prioritize “account creation + persistence” first.

### 8) Sprint Review

Was the sprint goal achieved? Yes.
 Why? The database migration was completed and verified through connection + validation checks, which unblocks authentication and persistence features.

Acceptance testing by Product Owner: feedback

- PO verified migration deliverable is complete (DB exists, app can connect, basic validation evidence provided).

- (If you need a sentence to paste as PO feedback: “Database successfully migrated and ready for integration with login/register and credit systems.”)

Adjustments planned (Product)

- Next sprint: complete login/register logic and ensure accounts are saved and retrieved from the migrated database.

- Begin DB extension planning for avatar customization inventory (loot crates/clothes) after core auth persistence is stable.

Revised Definition of Done (DoD)
 For database/infrastructure PBIs, “Done” requires:

- DB migration completed and committed

- App connects successfully using migrated DB

- Basic validation checklist completed (schema + sample queries)

- Evidence attached (screenshots/logs) + Trello updated

Sprint review summary

- Sprint 2 delivered the core infrastructure milestone (migrated DB). The team is now positioned to implement authentication persistence and future features that depend on the database.

### 9) Sprint Retrospective

Adjustments planned (Process)

- Add buffer time for high-risk infrastructure tasks (migration/testing).

- Establish story points and track velocity starting next sprint.

- Require an “integration checkpoint” mid-sprint (connect app + run smoke test early).

Sprint retrospective summary

- Communication and alignment were strong, but estimation for DB migration was optimistic. Earlier smoke testing and better buffering will reduce schedule compression on dependent tasks.

Team velocity tracked through sprints

- Sprint 2 completed: 1 major PBI (“Migrate the db”)

- Note: Story points not fully implemented yet; velocity tracked by completed PBIs/tasks.

### 10) Backlog Grooming Activity Summary

Grooming summary

- Reviewed backlog/user stories for: earning credits and wagering, daily login rewards, leaderboard, avatar customization, friend code system, and private lobby.

- Confirmed migration must precede these items; reprioritized auth + credits persistence next.

PBIs added/removed/reprioritized

- Reprioritized: Login/Register DB persistence to next sprint (Sprint 3).

- Added/planned: Avatar customization inventory and loot crates (clothing unlocks) as a future DB extension after authentication is stable.

Definition of Ready (DoR)
 A backlog item is “Ready” when:

- User story + acceptance criteria are written

- Dependencies identified (DB tables/fields needed listed)

- Owner assigned

- Estimate provided (time or story points)

- Validation/testing expectation defined

### 11) Two Daily Scrum Meeting Summaries

Daily Scrum #1 (early Sprint 2)

- CB (Scrum Master): Migration work underway; finalizing schema + preparing environment. Next: execute migration and start validation. Blockers: none.

- MW: Continued UI work and prepared to integrate once DB is stable. Next: help test integration.

- SM: Worked on game planning/logic breakdown aligned to betting/credits. Next: build skeleton logic modules.

- LL: Supported structure/routing planning for future auth pages. Next: assist with UI integration.

- RD: Documented game needs for credits/wagers and future leaderboard hooks. Next: support testing/requirements.

Daily Scrum #2 (later Sprint 2)

- CB (Scrum Master): DB migrated; app connection configured; smoke tests completed. Next: support login/register persistence + begin planning DB extension for loot crates/clothes.

- MW: Ready to connect UI pages to DB-backed auth once persistence code is in place. Next: coordinate with CB.

- SM: Continued game logic pieces; next: link outcomes to credits after auth is storing accounts.

- LL: Continued UI support and planning for avatar customization workflow. Next: help once DB tables exist.

- RD: Continued requirements for credits/leaderboard; next: assist with implementation/testing.

### 12) Link to Project GitHub Repo

GitHub Repo: https://github.com/SamMccorke1/SE2-Project---Casino.git

### 13) Attendance of Each Member During Two Class Sessions for Current Sprint

(Fill the team rows if required; your attendance is included per your note.)

| Member |  |  |
| --- | --- | --- |
| Caleb Blevins (CB) | Present |
| Samuel McCorkel (SM) | Present |
| Matthew Williams (MW) | Present |
| Lucas Litzenberger (LL) | Present |
| Rio Day (RD) | Present |